## Risk Register
Risk Register
Cyber, Operational & Compliance Risk Portfolio — Enterprise Risk Register
ID | Risk Description | Category | Likelihood | Impact | Inherent Rating | Existing Controls | Treatment Plan | Treatment Type | Owner | Residual Likelihood | Residual Impact | Residual Rating | Target Date | Inherent Band | Residual Band | Residual Rank
R01 | Phishing attack leads to compromised employee credentials, enabling unauthorised system access. | Cyber | 4 | 4 | 16 | C01, C02 | Roll out mandatory quarterly phishing simulations; enforce MFA on all cloud and email accounts. | Treat | Head of IT Security | 2 | 3 | 6 | 2026-11-30 | Critical | Low | 2
R02 | Ransomware infection encrypts production systems, halting business operations. | Cyber | 3 | 5 | 15 | C02, C03, C10 | Deploy EDR across all endpoints; validate immutable, offline backups with quarterly restore tests. | Treat | Head of IT Security | 2 | 4 | 8 | 2026-12-15 | High | Medium | 1
R03 | Unpatched critical vulnerabilities on internet-facing systems are exploited by threat actors. | Cyber | 3 | 4 | 12 | C04 | Implement 14-day SLA for critical patches; add continuous external vulnerability scanning. | Treat | IT Infrastructure Manager | 2 | 3 | 6 | 2026-11-15 | Medium | Low | 3
R04 | Malicious or negligent insider exfiltrates sensitive customer or financial data. | Cyber | 2 | 5 | 10 | C05, C11 | Deploy DLP on email and endpoints; enforce least-privilege access reviews every 6 months. | Treat | Head of IT Security | 1 | 4 | 4 | 2027-01-31 | Medium | Low | 5
R05 | Cloud storage misconfiguration exposes sensitive data to the public internet. | Cyber | 3 | 4 | 12 | C06 | Enable CSPM tooling with automated alerts and remediation playbooks for public storage exposure. | Treat | Cloud Platform Owner | 1 | 4 | 4 | 2026-10-31 | Medium | Low | 6
R06 | Loss of key personnel results in loss of critical operational or technical knowledge. | Operational | 3 | 3 | 9 | C07 | Document critical processes; implement cross-training and formal succession plans for key roles. | Treat | Head of Operations | 2 | 2 | 4 | 2027-02-28 | Medium | Low | 7
R07 | Inadequate disaster recovery plan leads to extended downtime after a major incident. | Operational | 2 | 5 | 10 | C08, C10 | Formalise and test DR plan annually; define and validate RTO/RPO targets with the business. | Treat | Head of IT Infrastructure | 1 | 4 | 4 | 2027-03-31 | Medium | Low | 8
R08 | Disruption at a single-source critical supplier halts a core business process. | Operational | 3 | 4 | 12 | C09 | Identify and qualify secondary suppliers for critical inputs; build contingency stock where feasible. | Treat | Procurement Lead | 2 | 3 | 6 | 2027-01-15 | Medium | Low | 4
R09 | Inadequate backup procedures result in permanent loss of business-critical data. | Operational | 2 | 4 | 8 | C10 | Automate daily backups with quarterly restore testing and offsite/immutable copies. | Treat | IT Infrastructure Manager | 1 | 3 | 3 | 2026-11-30 | Medium | Low | 12
R10 | Physical security breach at office or data centre leads to theft, damage, or unauthorised access. | Operational | 2 | 3 | 6 | C11 | Upgrade badge access control and CCTV coverage; introduce formal visitor management process. | Treat | Facilities Manager | 1 | 2 | 2 | 2027-02-15 | Low | Low | 13
R11 | Non-compliance with GDPR / data protection requirements results in regulatory fines and reputational harm. | Compliance | 3 | 5 | 15 | C12, C14 | Conduct DPIAs for all new processing activities; appoint DPO and run annual compliance audit. | Treat | Data Protection Officer | 1 | 4 | 4 | 2026-12-31 | High | Low | 9
R12 | Failure to meet industry regulatory reporting deadlines results in penalties or sanctions. | Compliance | 2 | 3 | 6 | C13 | Implement a centralised compliance calendar with automated reminders and owner sign-off. | Treat | Compliance Manager | 1 | 2 | 2 | 2026-10-31 | Low | Low | 14
R13 | Inadequate records retention practices cause failure to produce records for e-discovery or audit. | Compliance | 2 | 3 | 6 | C14 | Publish records retention and disposal schedule; train staff and audit compliance annually. | Treat | Compliance Manager | 1 | 2 | 2 | 2027-01-31 | Low | Low | 15
R14 | Non-compliance with PCI DSS in handling payment card data leads to fines and loss of processing rights. | Compliance | 2 | 5 | 10 | C15 | Segment cardholder data environment; encrypt data in transit and at rest; complete annual PCI audit. | Treat | Head of IT Security | 1 | 4 | 4 | 2027-03-15 | Medium | Low | 10
R15 | Inadequate due diligence on third parties results in onboarding vendors with unacceptable risk exposure. | Compliance | 3 | 3 | 9 | C16 | Mandate security and compliance questionnaires before onboarding; review high-risk vendors annually. | Tolerate | Procurement Lead | 2 | 2 | 4 | 2027-04-30 | Medium | Low | 11
Legend:
Blue-outlined columns (Likelihood, Impact, Residual Likelihood, Residual Impact, Existing Controls, Treatment Plan/Type, Owner, Target Date) are the editable inputs.
Inherent/Residual Rating = Likelihood x Impact (auto-calculated). Band thresholds: Low 1-5, Medium 6-10, High 11-15, Critical 16-25.
Existing Controls references Control IDs from the Control Library tab (e.g. C02 = Multi-Factor Authentication).

## Scoring Scale
Scoring Scale
Definitions used to score Likelihood and Impact across the Risk Register (1 = lowest, 5 = highest)
Score | Likelihood Definition | Impact Definition
1 | Rare — may occur only in exceptional circumstances (e.g. less than once every 5 years) | Negligible — minimal disruption; no material financial or reputational impact
2 | Unlikely — could occur at some point (e.g. once every 2-5 years) | Minor — limited disruption; low financial impact; no external visibility
3 | Possible — might occur at some point (e.g. roughly once a year) | Moderate — noticeable disruption; moderate financial impact; some stakeholder or media attention
4 | Likely — will probably occur (e.g. multiple times per year) | Major — significant disruption; high financial impact; regulatory or senior management attention
5 | Almost Certain — expected to occur, possibly frequently (e.g. monthly or more often) | Severe — critical disruption to operations; severe financial/reputational impact; potential regulatory or legal action
Rating bands used throughout this workbook: Inherent/Residual Rating = Likelihood x Impact.
Low 1-5, Medium 6-10, High 11-15, Critical 16-25.

## Control Library
Control Library
Reusable catalogue of controls referenced by ID in the Risk Register
Control ID | Control Name | Category | Description | Effect
C01 | Security Awareness Training | Administrative | Mandatory staff training and simulated phishing exercises to reduce susceptibility to social engineering. | Reduces likelihood
C02 | Multi-Factor Authentication (MFA) | Technical | MFA enforced on email, VPN, cloud administration and other critical systems. | Reduces likelihood
C03 | Endpoint Detection & Response (EDR) | Technical | Automated detection, containment and response to malware and ransomware on endpoints. | Reduces impact
C04 | Patch Management Programme | Technical | Scheduled vulnerability scanning and a defined SLA for patching critical systems. | Reduces likelihood
C05 | Data Loss Prevention (DLP) | Technical | Monitors and blocks unauthorised transfer of sensitive data via email, web and removable media. | Both
C06 | Cloud Security Posture Management (CSPM) | Technical | Continuous automated scanning of cloud environments for misconfigurations and public exposure. | Reduces likelihood
C07 | Succession Planning & Cross-training | Administrative | Documented knowledge transfer and backup coverage for roles holding critical knowledge. | Reduces impact
C08 | Business Continuity / DR Plan | Administrative | Documented and tested continuity plan with defined recovery time and point objectives. | Reduces impact
C09 | Supplier Risk Assessment | Administrative | Due diligence, criticality rating and contingency planning for key suppliers. | Both
C10 | Backup & Recovery Testing | Technical | Automated, immutable backups with scheduled restore testing to confirm recoverability. | Reduces impact
C11 | Physical Access Control | Physical | Badge access, CCTV monitoring and visitor management at offices and data centres. | Reduces likelihood
C12 | Data Protection Impact Assessments (DPIA) | Administrative | Structured privacy risk assessment performed before new personal data processing begins. | Reduces likelihood
C13 | Compliance Calendar & Tracking | Administrative | Centralised register of regulatory deadlines with automated reminders and owner sign-off. | Reduces likelihood
C14 | Records Retention Policy | Administrative | Defined retention and disposal schedules covering all major record types. | Both
C15 | PCI DSS Segmentation & Encryption | Technical | Network segmentation of the cardholder data environment with encryption in transit and at rest. | Both
C16 | Third-Party Due Diligence Programme | Administrative | Security and compliance questionnaires and risk scoring completed before vendor onboarding. | Reduces likelihood

## Risk Appetite
Risk Appetite
Statement of the level of risk the organisation is willing to accept in pursuit of its objectives
The organisation has a low appetite for data breaches and regulatory non-compliance, given the potential for significant financial penalties, legal exposure and reputational harm. It has a moderate appetite for operational risk, accepting a degree of disruption where it is well controlled and does not threaten continuity of core services. It has a higher appetite for innovation-related risk, recognising that experimentation and controlled risk-taking are necessary to remain competitive and to support business growth.
Appetite to Tolerance Mapping
Risk Category | Appetite Level | Residual Rating Tolerance | Escalation Trigger
Data breaches / regulatory compliance | Low | Residual rating must be Low (1-5) | Any residual rating above 6 escalated to the Board within 5 business days
Operational risk | Moderate | Residual rating up to Medium (6-10) accepted with active monitoring | Any residual rating above 12 escalated to senior management
Innovation-related risk | Higher | Residual rating up to High (11-15) accepted to support growth initiatives | Residual rating above 15 requires Executive Committee sign-off

## Methodology
Methodology
How this risk portfolio was built
Inherent vs. Residual Risk
• Inherent risk is scored assuming no controls are in place; it reflects the raw likelihood and impact of the risk event.
• Residual risk is scored after considering the existing controls listed in the Risk Register, reflecting the risk that remains once those controls are applied.
• Both are calculated the same way (Likelihood x Impact) so they can be compared directly and the risk reduction achieved by controls is visible.
Likelihood x Impact Scoring
• Each risk is scored on a 1-5 scale for both Likelihood and Impact, as defined on the Scoring Scale tab.
• The Rating is calculated as Likelihood x Impact, producing a score from 1 to 25.
• Scores are grouped into three bands for reporting: Low (1-5), Medium (6-10), High (11-15) and Critical (16-25).
How Appetite Influenced Treatment Decisions
• Risks in categories where the organisation has low appetite (e.g. data breaches, regulatory compliance) were treated down to a Low residual rating wherever practicable.
• Risks in categories with moderate or higher appetite (e.g. general operational risk) were treated to a Medium residual rating where further reduction was not cost-justified.
• Where residual risk already sat within the organisation's stated tolerance and further treatment cost outweighed the benefit, the risk was tolerated rather than further treated (e.g. R15).
How Controls Were Selected
• Controls were drawn from the Control Library tab, which catalogues reusable technical, administrative and physical controls.
• Each risk references the specific Control ID(s) that materially reduce its likelihood and/or impact.
• Controls were selected to target the dominant driver of each risk: likelihood-reducing controls (e.g. MFA, patching) for risks driven by exposure, and impact-reducing controls (e.g. backups, DR planning) for risks driven by consequence severity.
How the 15 Risks Were Scored
• Risks were identified across three categories — Cyber, Operational and Compliance — with five risks in each to give a balanced portfolio.
• Likelihood and Impact were scored based on typical industry incident frequency and severity benchmarks for each risk type.
• Residual scores were then derived by estimating the effect of the existing/planned controls on the inherent score.
How the Heat Map and Dashboard Were Built
• The Heat Map tab uses COUNTIFS formulas to count how many risks fall into each of the 25 Likelihood x Impact combinations, based on inherent scores from the Risk Register.
• Cells are colour-coded Low/Medium/High/Critical using the same rating bands applied throughout the workbook.
• The Dashboard tab uses COUNTIFS and RANK formulas to summarise risk counts by category, by rating band, by treatment status, and to surface the top 3 risks by residual rating, with supporting bar and pie charts.

## Dashboard
Dashboard
Portfolio summary — 15 risks across Cyber, Operational & Compliance
Risks by Category |  |  | Residual Risk by Rating Band
Category | Count |  | Band | Count
Operational | 5 |  | Low | 14
Cyber | 5 |  | Medium | 1
Compliance | 5 |  | High | 0
Treatment Status |  |  |  | Top 3 Risks by Residual Rating
Treatment Type | Count | % of Total |  | Rank | ID | Risk Description | Residual Rating
Treat | 14 | 93% |  | 1 | R02 | Ransomware infection encrypts production systems, halting business operations. | 8
Tolerate | 1 | 6.667% |  | 2 | R01 | Phishing attack leads to compromised employee credentials, enabling unauthorised system access. | 6
Transfer | 0 | 0% |  | 3 | R03 | Unpatched critical vulnerabilities on internet-facing systems are exploited by threat actors. | 6
Terminate | 0 | 0%

## Heat Map
Heat Map
Inherent risk heat map — count of risks by Likelihood x Impact combination
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 1 | 0
3 | 0 | 0 | 2 | 3 | 2
2 | 0 | 0 | 3 | 1 | 3
1 | 0 | 0 | 0 | 0 | 0
Impact →
Grid shows the count of risks (inherent Likelihood x Impact) from the Risk Register in each cell.
Colour key: Green = Low (1-6) Amber = Medium (7-12) Red = High (13-25) Dark red (16-25)

## Third-Party Register
Third-Party Register
Vendors and service providers with material exposure to the organisation
Vendor | Service | Criticality | Key Risks | Key Controls | Status
AWS | Cloud infrastructure hosting | Critical | Service outage; data breach via misconfiguration; concentration risk | CSPM monitoring (C06); contractual SLAs; DR plan across regions (C08) | Active
Payroll Provider | Outsourced payroll processing | Critical | Data breach of employee PII; processing errors; service disruption | Vendor due diligence (C16); encrypted data transfer; SLA monitoring | Active
IT Managed Service Provider | Helpdesk & infrastructure support | High | Privileged access misuse; inadequate incident response | Access reviews (C11); contractual security requirements; DPIA (C12) | Active
Payment Processor | Card payment processing | Critical | PCI DSS non-compliance; cardholder data exposure | Network segmentation & encryption (C15); annual PCI audit | Active
HR SaaS Platform | Core HR / people data system | High | Data breach of employee records; vendor lock-in | DPIA on onboarding (C12); due diligence questionnaire (C16) | Active
Microsoft 365 | Email & collaboration platform | Critical | Account compromise; data loss; phishing vector | MFA (C02); DLP (C05); security awareness training (C01) | Active
External Legal Counsel | Legal advisory services | Medium | Confidentiality breach; conflict of interest | NDA in place; access limited to named matters | Active
Marketing Agency | Digital marketing & campaign management | Low | Brand/reputational risk; limited data access | Contractual brand guidelines; annual review | Under Review